## Basic Gantt Chart
TEAM GANTT CHART TEMPLATE
Task Allocation.
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER
Part 1: Report configuration and Communications plan
| Configure Report structure | 2026-03-11 | 2026-03-24 | 1 | 14 | Đăng
| Write Introduction | 2026-03-11 | 2026-03-24 | 1 | 14 | Tuấn An
| The purpose of the work | 2026-03-11 | 2026-03-24 | 1 | 14 | Chí An
| Communications plan (txt,email, social media) | 2026-03-11 | 2026-03-24 | 1 | 14 | Chí An
| Document Share Plan (Dropbox, Gdrive etc..) | 2026-03-11 | 2026-03-24 | 1 | 14 | Đăng
Part 2: Assignment Problem and Scope
| Overview of the problem | 2026-03-11 | 2026-03-12 | 1 | 1 | Đăng
| Description of the proposed system | 2026-03-12 | 2026-03-13 | 2 | 1 | Chí An
| Identify constraints and limitations | 2026-03-12 | 2026-03-13 | 2 | 1 | Tuấn An
| Functional and Non-Functional List | 2026-03-12 | 2026-03-13 | 2 | 1 | Chí An
| Gathering Techniques | 2026-03-13 | 2026-03-14 | 3 | 1 | Đăng
Part 3: User story and Interface Review
| Stakeholder Identification | 2026-03-13 | 2026-03-15 | 3 | 2 | Tuấn An
| User story - key functional requirements | 2026-03-13 | 2026-03-14 | 3 | 1 | Tuấn An
| User story - acceptance criteria | 2026-03-14 | 2026-03-15 | 4 | 1 | Tuấn An
Part 4: Models
| Use case description | 2026-03-16 | 2026-03-18 | 6 | 2 | Chí An, Tuấn An
| System Sequence Diagram | 2026-03-18 | 2026-03-20 | 8 | 2 | Tuấn An
| State Machine Diagram | 2026-03-18 | 2026-03-20 | 8 | 2 | Chí An
| CRUD UI design | 2026-03-13 | 2026-03-15 | 3 | 2 | Đăng
| Interface Design Assets | 2026-03-15 | 2026-03-17 | 5 | 2 | Đăng
| CRUD Technique on event table | 2026-03-17 | 2026-03-20 | 7 | 3 | Đăng
Part 5: Test and presentation
| Test, review and research | 2026-03-20 | 2026-03-22 | 10 | 2 | Chí An
| Write a discussion (500 words) | 2026-03-22 | 2026-03-24 | 12 | 2 | Tuấn An
| Slide Presentation | 2026-03-20 | 2026-03-27 | 10 | 7 | Đăng
| Appendix Completion | 2026-03-11 | 2026-03-24 | 1 | 14 | All
Note on D4: Nelson Vargas: The assigment due date is the definitive end date. No tasks should go beyond this date.
Note on E7: Nelson Vargas: Start day, 0 = 24/09